## Sheet1
Task | Description | Details | Who | Start Time | End Time
Deployment Date: 5/21/09 Job Number: ORI6169 Description: Contact List Webservice - Targeting .NET 3.5 Framework, deploy Server[s] : OCAPP03, OCAPP04,OSQL01
Deploy Data Updates
OCSQL01 | Backup contact table
Use SQLManagment studio to update the table to increase the size of the 'language' column from the current value to [language] [nvarchar](15)
| verify that current ws works | view admin page
submit at least one contact form
remove added item from db
Deploy Webservice to new servers (IPFiltered)
Both | Create new app pool named OCWSAppPool | use the default app pool as the template
Create new app pool named OCWSAppPool
No backup needed - no service exists
Set IP Address and Domain Name Restrictions from IIS settings for the site Directory Security->IP address and name restrictions->Edit - see the current ws for settings
Set Application pool from IIS for the site Home->..
OCAPP03 | Deploy site to ocapp03 - xcopy deployment (D:\InetPub\ww1.ws.owenscorning.com\webroot)
Validate that the site is up -
navigate to the asmx page locally
navigate to the asmx page from hanson domain
navigate to the admin page - login in - view list
OCAPP04 | Deploy site to ocapp03 - xcopy deployment (D:\InetPub\ww1.ws.owenscorning.com\webroot)
Validate that the site is up -
navigate to the asmx page locally
navigate to the asmx page from hanson domain
navigate to the admin page - login in - view list
Deploy energy complte to new servers ocenergycomplete.com (IPFiltered)
Both | Create new app pool named OCEnergyCompleteAppPool | use the default app pool as the template
Create new app pool named OCEnergyCompleteAppPool
Set Application pool from IIS for the site Home->..
OCAPP03 | There is currently a default.htm page that redirects to insulation - this needs to stay there and be active until we officially go live
set up directory security for hanson only domain - see webservices deployment above
deploy site to D:\InetPub\ww1.ocenergycomplete.com\webroot
| verify site is up | navigate to /default.aspx
| smoke test | open all pages that are navigable
submit contact forms (4)
remove test data from service
check Omniture data transmission - no data will show up from Hanson Ips
OCAPP04 | There is currently a default.htm page that redirects to insulation - this needs to stay there and be active until we officially go live
set up directory security for hanson only domain - see webservices deployment above
deploy site to D:\InetPub\ww2.ocenergycomplete.com\webroot
| verify site is up | navigate to /default.aspx
| smoke test | open all pages that are navigable
submit contact forms (4)
remove test data from service
check Omniture data transmission - no data will show up from Hanson Ips
BOTH | update appsettings config - mail.debug = false - to activate emails
| Update SiteMap/Robots.txt |  | Charles/Dave?
Status pages (Nagios) | verify that status is being monitored |  | DaveA
Omniture | Validate Omniture Metrics are being collected |  | Jon
Smoke Test | General smoke testing |  | BM
Clean up
OSQL01 | remove test contacts from smoke test
drop the temp/back up table
Notify Client