## Sheet1
Task | Description | Details | Who | Start Time | End Time
Deployment Date: Job Number: Description: Server[s] : OCAPP03, OCAPP04
Deploy Data Updates | Create database on OCSQL02 | Run script "DB Reset & Create.sql" found in the Notification Service database directory | Matt
|  | Manually create the Site Configuration table | Matt
Build Project | Check out latest owenscorning.notificationservice, webservices.owenscorning.com, commercial.owenscorning.com |  | Matt
| Publish webservices.owenscorning.com locally |  | Matt
| make sure commercial.owenscorning.com builds |  | Matt
Deploy site to new servers (IPFiltered)
OCAPP03 | Backup commercial.owenscorning.com |  | Matt
| Backup ws.owenscorning.com |  | Matt
| Move the published webservice to the webservice directory |  | Matt
| Make deployment package for commercial |  | Matt
| Deploy commercial to the commercial site as a web site |  | Matt
| Validate commercial site | commercial.owenscorning-a.hansonstatus.com | Matt
OCAPP04 | Backup commercial.owenscorning.com |  | Matt
| Backup ws.owenscorning.com |  | Matt
| Move the published webservice to the webservice directory |  | Matt
| Make deployment package for commercial |  | Matt
| Deploy commercial to the commercial site as a web site |  | Matt
| Validate commercial site | commercial.owenscorning-b.hansonstatus.com | Matt
Status pages (Nagios)
Omniture
Smoke Test | Validate commercial site
Clean up | Remove backups |  | Matt
Notify Client